# Common Estimation Techniques

### 1. Work Breakdown Structure (WBS)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Testing tasks are broken down into smaller sub-tasks.

- Estimate each sub-task → then add them up.

✅ Example:

- Test Planning = 8 hrs

- Test Case Design = 20 hrs

- Test Execution = 40 hrs

- Defect Retesting = 12 hrs

- Total = 80 hrs

### 2. Expert Judgment

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Estimation based on the experience of senior testers or managers.

- Useful when similar projects were done before.

✅ Example:

- A test manager recalls a similar e-commerce project took ~200 hrs.

- Adjusts based on new complexity → 220 hrs.

### 3. Three-Point Estimation (PERT Technique)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

Uses 3 values to calculate realistic estimates:

- O (Optimistic) – best case

- M (Most Likely) – normal case

- P (Pessimistic) – worst case

Formula:

Estimate=O+4M+P6\text{Estimate} = \frac{O + 4M + P}{6}

✅ Example:

- O = 10 hrs, M = 15 hrs, P = 30 hrs

- Estimate = (10 + 4×15 + 30) ÷ 6 = 16.67 hrs

### 4. Function Point Analysis (FPA)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Estimates effort based on functionality size (inputs, outputs, user interactions, files, etc.).

- More functionality → more testing effort.

✅ Example:

- Login (5 pts), Payment (10 pts), Reporting (15 pts).

- Total = 30 Function Points → 3 hrs per FP = 90 hrs testing.

### 5. Use Case Point (UCP)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Similar to FPA but based on use cases.

- Factors in complexity of actors & transactions.

✅ Example:

- Simple Actor = 1 pt, Complex Actor = 3 pts.

- Simple Use Case = 5 pts, Complex Use Case = 15 pts.

- Multiply by productivity factor → final estimate.

### 6. Test Point Analysis

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Special for test cases.

- Effort is based on number of test cases × complexity factor.

✅ Example:

- 100 test cases × 1 hr each = 100 hrs.

- If 20% are complex → +20 hrs.

- Total = 120 hrs.

### 7. Wideband Delphi Technique

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- A group of experts give estimates independently.

- Then discuss differences and refine until consensus is reached.

✅ Example:

- Expert A: 150 hrs, Expert B: 200 hrs, Expert C: 180 hrs → After discussion, agree on 185 hrs.

### 8. Matrix-Based Technique

# Source: Chatgot (GPT-5-Standard) at [8/24/2025]

Uses a matrix of features/modules vs. complexity/risk levels to assign effort.

✅ Example:

| Module | Low | Medium | High |
| --- | --- | --- | --- |
| Feature A | 2 hr | 4 hr | 6 hr |
| Feature B | 3 hr | 6 hr | 9 hr |

If Feature A = High → 6 hrs, Feature B = Medium → 6 hrs → Total = 12 hrs

### 9. Ratio-Based Estimation

# Source: Chatgot (GPT-5-Standard) at [8/24/2025]

Uses historical ratios between development and testing from similar projects.

✅ Example:
 Previous project ratio = 1:0.4 (Dev:Test)
 If Dev = 1000 hrs → Testing = 400 hrs

### 10. Extrapolation Estimation Technique

# Source: Chatgot (GPT-5-Standard) at [8/24/2025]

Uses actual completed work to estimate remaining effort.

✅ Example:
 First 50 test cases = 80 hrs → For 200 cases →
 Estimate = (80 ÷ 50) × 200 = 320 hrs

### 11. Percentage of Development Effort

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Testing is estimated as a fixed percentage of development time.

✅ Example:

- If development = 1000 hrs, testing = 30% → 300 hrs.

# Scenario Used for All Techniques

# Source: Chatgot (GPT-5-Standard) at [8/24/2025]

🔥 Perfect! I’ll create a comprehensive side-by-side comparison table where all 11 estimation techniques are applied to the same project scenario.

### ✅ Scenario Used for All Techniques

# Source: Chatgot (GPT-5-Standard) at [8/24/2025]

- Project: E-commerce Website

- Development Effort: 1,000 hrs

- Modules: Login, Product Catalog, Payment, Reports

- Complexity Assumptions:

  - Login → Low

  - Product Catalog → Medium

  - Payment → High

  - Reports → High

- Total Test Cases: 200

- Complexity Mix: 20% complex

- Productivity Factor: 20 hrs per Use Case Point

- Function Points: Login (5), Payment (10), Reports (15) = 30 FP

- Use Case Points: 40 UCP

### ✅ Comparison Table (All 11 Techniques)

# Source: Chatgot (GPT-5-Standard) at [8/24/2025]

| Technique | Formula / Basis | Estimate |
| --- | --- | --- |
| 1. WBS | Sum of detailed tasks | 80 hrs |
| 2. Expert Judgment | Based on similar past projects | 220 hrs |
| 3. PERT (Three-Point) | (O + 4M + P) / 6 → O=10, M=15, P=30 | 16.7 hrs per task → ~200 hrs total |
| 4. Function Point | FP × Productivity (3 hrs/FP) | 30 FP × 3 = 90 hrs |
| 5. Use Case Point | UCP × Productivity Factor | 40 × 20 = 800 hrs |
| 6. Test Point Analysis | #TC × Avg Time + Complexity Factor | 200 × 1 + (20% × 200 × 0.5) = 240 hrs |
| 7. Wideband Delphi | Expert consensus | 185 hrs |
| 8. % of Dev Effort | Dev Effort × % (30%) | 1,000 × 0.3 = 300 hrs |
| 9. Matrix-Based | Sum of module complexity-based estimates | 140 hrs |
| 10. Ratio-Based | Dev Effort × Historical Ratio (0.4) | 1,000 × 0.4 = 400 hrs |
| 11. Extrapolation | Completed cases scaled up | 80 hrs for 50 cases → (80 ÷ 50) × 200 = 320 hrs |

✅ Key Insights:

- Lowest Estimate: WBS (80 hrs) – because we assumed minimal tasks.

- Highest Estimate: UCP (800 hrs) – very conservative.

- Balanced Methods: % of Dev Effort (300 hrs), Test Point Analysis (240 hrs), Matrix (140 hrs).

🔥 Next Step Options:
 ✔ 1. Create a clean, color-coded Excel table + Graph (Bar Chart) showing all 11 estimates.
 ✔ 2. Generate a downloadable PDF summary (detailed explanation of each method + table + chart).
 ✔ 3. Make a Visual Infographic (for quick reference).

👉 Which one do you want first: Excel file + Chart, PDF, or Infographic?