# Three-Point Estimation

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

Excellent question 👍 — Three-Point Estimation is a widely used estimation technique in project management and software testing that helps reduce uncertainty.

## 📌 Definition of Three-Point Estimation

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

Three-Point Estimation is a technique where you estimate effort/duration/cost using three scenarios instead of a single guess:

- Optimistic (O): Best-case scenario (everything goes smoothly).

- Most Likely (M): Realistic scenario (normal conditions, most probable effort).

- Pessimistic (P): Worst-case scenario (risks, issues, delays).

## 🧮 Formula

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

There are two variations commonly used:

### 1. Simple Average Method

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

E=O+M+P3E = \frac{O + M + P}{3}

- Straightforward average of the three estimates.

### 2. PERT Weighted Average Method

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

(Project Evaluation and Review Technique)

E=O+(4M)+P6E = \frac{O + (4M) + P}{6}

- Gives more weight to the "Most Likely" estimate.

- Widely used in software testing & project management.

## 📊 Example: Testing a Login Module

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Optimistic (O): 10 hours (if no blockers, smooth execution).

- Most Likely (M): 16 hours (normal case).

- Pessimistic (P): 28 hours (environment issues, many bugs).

### Simple Average:

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

E=(10+16+28)/3=18 hrsE = (10 + 16 + 28) / 3 = 18 \text{ hrs}

### PERT Weighted Average:

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

E=(10+(4×16)+28)/6=17 hrsE = (10 + (4 \times 16) + 28) / 6 = 17 \text{ hrs}

👉 The testing team would plan ~17 hours for this task.

## 🎯 Advantages

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Considers uncertainty and risk.

- More realistic than single-point estimation.

- Reduces over-optimism (common in projects).

- Helps in risk analysis (difference between P and O shows uncertainty).

## ⚠️ Disadvantages

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Requires experience/expert input to define O, M, P.

- More effort than quick ratio-based estimates.

## 🔑 When Used in Testing

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Estimating effort for test case design.

- Planning test execution timelines.

- Estimating bug-fixing & re-testing cycles.

- Useful in Agile story point estimation.

✅ Summary:
 Three-Point Estimation = O, M, P → combine → average/PERT formula → realistic estimate.