# Estimation Techniques

## 📌 What are Estimation Techniques?

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

Estimation Techniques in software testing are methods used to predict the effort, time, cost, and resources needed for testing activities.

👉 In short:
 They help answer “How long will testing take?” and “How many people/resources are needed?”

Good estimation helps in:

- Planning test activities

- Allocating resources

- Setting realistic deadlines

- Managing risks and costs

## 🎯 Common Estimation Techniques in Software Testing

### 1. Work Breakdown Structure (WBS)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Testing tasks are broken down into smaller sub-tasks.

- Estimate each sub-task → then add them up.

✅ Example:

- Test Planning = 8 hrs

- Test Case Design = 20 hrs

- Test Execution = 40 hrs

- Defect Retesting = 12 hrs

- Total = 80 hrs

### 2. Expert Judgment

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Estimation based on the experience of senior testers or managers.

- Useful when similar projects were done before.

✅ Example:

- A test manager recalls a similar e-commerce project took ~200 hrs.

- Adjusts based on new complexity → 220 hrs.

### 3. Three-Point Estimation (PERT Technique)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

Uses 3 values to calculate realistic estimates:

- O (Optimistic) – best case

- M (Most Likely) – normal case

- P (Pessimistic) – worst case

Formula:

Estimate=O+4M+P6\text{Estimate} = \frac{O + 4M + P}{6}

✅ Example:

- O = 10 hrs, M = 15 hrs, P = 30 hrs

- Estimate = (10 + 4×15 + 30) ÷ 6 = 16.67 hrs

### 4. Function Point Analysis (FPA)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Estimates effort based on functionality size (inputs, outputs, user interactions, files, etc.).

- More functionality → more testing effort.

✅ Example:

- Login (5 pts), Payment (10 pts), Reporting (15 pts).

- Total = 30 Function Points → 3 hrs per FP = 90 hrs testing.

### 5. Use Case Point (UCP)

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Similar to FPA but based on use cases.

- Factors in complexity of actors & transactions.

✅ Example:

- Simple Actor = 1 pt, Complex Actor = 3 pts.

- Simple Use Case = 5 pts, Complex Use Case = 15 pts.

- Multiply by productivity factor → final estimate.

### 6. Test Point Analysis

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Special for test cases.

- Effort is based on number of test cases × complexity factor.

✅ Example:

- 100 test cases × 1 hr each = 100 hrs.

- If 20% are complex → +20 hrs.

- Total = 120 hrs.

### 7. Wideband Delphi Technique

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- A group of experts give estimates independently.

- Then discuss differences and refine until consensus is reached.

✅ Example:

- Expert A: 150 hrs, Expert B: 200 hrs, Expert C: 180 hrs → After discussion, agree on 185 hrs.

### 8. Percentage of Development Effort

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Testing is estimated as a fixed percentage of development time.

✅ Example:

- If development = 1000 hrs, testing = 30% → 300 hrs.

## 📊 Comparison of Estimation Techniques

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

| Technique | When to Use | Pros | Cons |
| --- | --- | --- | --- |
| WBS | Clear scope | Detailed & accurate | Time-consuming |
| Expert Judgment | Early stage | Quick, uses experience | Can be biased |
| Three-Point (PERT) | With uncertainty | Considers risks | Needs range estimates |
| Function Point Analysis | Large systems | Objective, standardized | Complex to apply |
| Use Case Points | Use-case-driven projects | Focus on functionality | Requires detailed use cases |
| Test Point Analysis | Based on test cases | Easy & practical | Needs test case count |
| Wideband Delphi | Collaborative | Reduces bias | Time-consuming |
| % of Development Effort | Early rough estimate | Fast & simple | Not always accurate |

## 🔑 Summary

# Source: Chatgot (GPT-5-Standard) at [8/17/2025]

- Estimation = predicting testing effort, time, cost, resources.

- Techniques include: WBS, Expert Judgment, Three-Point, FPA, UCP, Test Point, Wideband Delphi, % of Dev Effort.

- Choice depends on project size, available data, and uncertainty.